## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE MINDSCAPE: AN AI-POWERED STUDY COMPANION INTEGRATING NLP ALGORITHMS | [6 empty] | INSTITUTE NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY
PROJECT GUIDE PROF. SHEETAL JADHAV | [6 empty] | DEPARTMENT NAME | [6 empty] | COMPUTER SCIENCE AND ENGINEERING DATA SCIENCE
[7 empty] | DATE | [6 empty] | 2024-04-11
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [39 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Rutuja Patil, Tanvi Panchal, Riya Sawant, Sneha Sabat | 2024-01-01 | 2024-01-14 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Sneha Sabat, Riya Sawant, Rutuja Patil, Tanvi Panchal | 2024-01-15 | 2024-01-17 | 1 | 100% | bar: WEEK 3 M to WEEK 3 F
1.3 | Discussing the project topic with the help of paper prototype. | Rutuja Patil, Sneha Sabat | 2024-01-18 | 2024-01-25 | 1 | 100% | bar: WEEK 4 M to WEEK 5 F
1.4 | Designing the Graphical User Interface(GUI) | Tanvi Panchal, Riya Sawant | 2024-01-25 | 2024-02-04 | 3 | 100% | bar: WEEK 5 M to WEEK 7 F
1.5 | Presentation I | Rutuja Patil, Tanvi Panchal, Riya Sawant, Sneha Sabat | 2024-03-12 | 2024-03-12 | 1 | 100% | bar: WEEK 8 M to WEEK 8 F
2 | Project Design and Implementation
2.1 | Working of modules generating transcription | Rutuja Patil, Tanvi Panchal, Riya Sawant, Sneha Sabat | 2024-02-05 | 2024-03-10 | 1 | 100% | bar: WEEK 9 M to WEEK 9 F
2.2 | Working of modules generating summarized and in-depth notes | Rutuja Patil, Riya Sawant | 2024-03-01 | 2024-03-24 | 1 | 100% | bar: WEEK 10 M to WEEK 11 F
2.3 | Integration of all modules and Report Writing | Rutuja Patil, Riya Sawant, Tanvi Panchal, Sneha Sabat | 2024-03-25 | 2024-04-11 | 1 | 100%
2.4 | Presentation II | Rutuja Patil, Tanvi Panchal, Riya Sawant, Sneha Sabat | 2024-04-12 | 2024-04-12 | 2 | 100% | bar: WEEK 11 M to WEEK 13 F